MINUTES

Meeting	Emergency Plan Team
Date	18th October 2013
Venue	Southwell Fire Station
Present	RF Rob Fisher, Nottinghamshire County Council (NCC) / RM Richard Morgan, Southwell Flood Forum (SFF) / DS David Sheard, SFF / JF Josephine French, SFF / JP James Parker, SFF
Apologies
1	Flood Warden recruitment / - key points of wording noted / - email or call every volunteer registered / - articles in Bramley and Advertiser / - SFF newsletter / - copies of newsletter/separate flyer in library, shops, pubs etc / - add Brackenhurst Liaison Officer to contact list
2	Community areas – road closures / RF has spoken to Highways re: community road closure, they’re very keen, / happy to train volunteers. / Wardens must be named and roads identified first. / There is a small amount of finance available for kit BUT many communities / applying, first come first served. Lowdham may be priority. / Lucy Jarvis Environment Agency (EA) is happy to train volunteers, the more / the better. / NB: Road closures must be only to avoid / a) danger to motorists or / b) danger of bow waves damaging properties / Pinpointed 14 potential road closure sites in 3 areas: / Halloughton Road/Nottingham Road area / Church Street/Easthorpe area / Halam Hill area
3	Resilience store tools, materials - deferred
4	House defence products – deferred
5	Skeleton Plan / - in progress
6	Group structure / - will evolve
7	Communication / JP - possibility of using multiple broadcast text messages via free server for emergency communication. Discuss further. / Pagers for key contacts? / Mobile networks failure 23 July? usage overload or other problem? / Possibility of boosting coverage in emergency situation?

ACTION POINTS
Action	Who	By when
Flood Warden recruitment	JP	Next mtg
Transfer road closure sites to Flood Signage Scheme template	DS	Next mtg
Update Highways of our progress	RF	Next mtg
Contact all network providers.	JP	Next mtg